## Sheet3
Phase 1
| Topic | Status | Remarks | Assignned Developer
Partner Registration | Company Registration | Complete |  | Prathibha
| Company Details | Complete |  | Prathibha
| Tax Document | Pending
| Partner will Recieve an email with credentials | Pending
| Admin approves the Partner Registartion | Pending |  | Rama Krishna
Aggremet Generation | Add Contract Period | Pending
| Add Product | Complete |  | Bhaskar
| Add Discount | Pending
| Add additional terms & conditions | Pending
| Generate agreements | Pending
Parrtner Agreement Signed | Patner has to sign in the agreements and upload in DMS | Pending |  | Shiva
| Admin will review the agreement signed and approved | Pending |  | Shiva
Cybrillance/NeuShield agreement Signed | Cybrillance has to sign in the agreements and upload in DMS | Pending | signnature completed
| NeuShield has to sign in the agreements and uplod in the DMS | Pending
| Cybrillance has successfully onboarded the partner | Pending
Prospects | Add a Prospect | Pending | Bulk Insert not completed
| Select Product | Pending
| Add Prospect Stages | Pending
| Generate Quotes | Pending
Client | Update Stages | Pending
| Update Payment terms | Pending
| Generate Invoice | Pending
| Uppdate payment Details send it to Cybrillance admin for apprval | Pending
Payment & License Update | Payment is approved by admin | Pending
| NeuShied admin has to upload the license | Pending
| Update partner license issued | Pending
| Dashoard update | Pending
Dms Role | Partners Role | Pending
| Super Admin Role | Complete |  | Sagar
| NeShield Role | Pending
| Aligment/Layout | Pending |  | Rama Krishna